## PSM I Practice Test 1
Question | Question Type (multiple-choice or multi-select) | Answer Option 1 | Answer Option 2 | Answer Option 3 | Answer Option 4 | Answer Option 5 | Answer Option 6 | Correct Response | Explanation | Knowledge Area
To effectively track the Sprint progress, Scrum mandates | multiple-choice | Preparing Sprint burn down charts | Increasing the transparency by frequently updating the remaining work | Earned Value approach |  |  |  | 2 | Scrum does not mandate techniques like Sprint burn down or earned value. However, it stresses bringing in highest transparency of the underlying information behind Scrum artifacts. | PSM I Assessment
For the Product Backlog Refinement act, the Scrum Team needs to define a recurring pre-set time every week outside the current working hours of the Developers. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | This is an ongoing act that happens within the hours of current Sprint. The time can be mutually discussed and agreed by Product Owner and the Developers. Usually it does not take more than 10% capacity of the Developers. Also, Product Backlog Items can be updated at any time by the Product Owner or at the Product Owner’s discretion. | PSM I Assessment
A short expression of the purpose of a Sprint which is often a business need– is called | multiple-choice | Sprint Goal | Acceptance Criteria | Definition of Done |  |  |  | 1 | Sprint Goal is the purpose of the Sprint and hence needs to be preserved. The Sprint Goal gives the Developers some flexibility regarding the functionality implemented within the Sprint. | PSM I Assessment
The Product Owner provides the transparency of their product plan to the stakeholders and the Scrum Team through | multiple-choice | Planning Backlog | Sprint Backlog | Project Backlog | Product Backlog |  |  | 4 | The Product Owner uses Product Backlog to update the stakeholders on the current state of the product plan. | PSM I Assessment
The Developers of a Scrum Team are often interrupted in the Sprint midway and assigned to work on “other” high priority items. Frequently, such interruptions lead to not meeting the Sprint Goal. The most likely cause could be | multiple-choice | The Developers are not technically competent | The Product Owner authority is ineffective or influenced by another authority | The Sprint Planning is poor |  |  |  | 2 | The Product Owner is the ultimate authority of the Product Backlog on which the Developers must work. Those wanting to change a Product Backlog item’s priority must address the Product Owner. For the Product Owner to succeed, the entire organization must respect his or her decisions. If the Developers are given different work, it indicates that Product Owner’s authority is interrupted. | PSM I Assessment
One of the major challenges for the team getting newly into Scrum can be | multiple-choice | Developing skills to produce useable Increment just within a short Sprint | Learning about Scrum terminology | Difficulty in getting adapted to Scrum tools |  |  |  | 1 | Scrum is lightweight with Scrum Teams and their associated simple roles, events, artifacts, and rules. But for new teams, it is difficult to master the skill to produce deployable and useable Increment within short Sprints. Scrum is not associated with any tools. | PSM I Assessment
Scrum Master forecasts the Product burn-down during Sprint Review. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | It is responsibility of the Product Owner to track the progress of the Product Backlog and forecasts the completion. This forecasting is done in every Sprint Review. | PSM I Assessment
Scrum allows having gaps between two subsequent Sprints, in which the team can accomplish support activities and team building activities | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | Sprints are done consecutively, without intermediate gaps. | PSM I Assessment
Multiple Scrum Teams are required to work on the same product. How can they integrate their development? | multiple-choice | by mutually working with each other to create an integrated Increment | by maintaining individual Product Backlog for each team | by setting up some common working sessions between the lead Developers of each team to merge their changes before the Sprint Review |  |  |  | 1 | Multiple teams working on the same product must have a single Product Backlog. It is the responsibility of all the teams to mutually define their Definitions of Done, and then work with each other so that they can create an integrated Increment that is valuable and useful. | PSM I Assessment
Select all that apply. Which Scrum events facilitate inspection and adaptation? | multiple-choice | Sprint | Backlog Refinement | Sprint Retrospective | Development Work |  |  | 3 | Other than the "Sprint," all other four events facilitate inspection and adaptation. Backlog Refinement is called as an Act within Scrum. | PSM I Assessment
Select all that apply. A Product Owner requests the Developers to help them with some tasks related to Product Backlog maintenance. | multi-select | The Scrum Master should step in and coach Product Owner to perform their job themselves | It is okay, but Product Owner is still accountable for the Product Backlog maintenance. | The Developers should refer Product Owner to speak with their manager | The Developers can volunteer if this additional task does not impact their Sprint work |  |  | 2,4 | The Product Owner may have the Developers help them with Product Backlog maintenance. However, the Product Owner remains accountable. There is no manager for the Developers within the Scrum Team. | PSM I Assessment
Velocity is an indication of team performance. It may be used by | multiple-choice | The Scrum Team an internal measure to plan and track their improvements. | The managers to do performance appraisals for the team | The organization to aggregate into organization level productivity |  |  |  | 1 | It is an optional standard, tracked by the Developers for use within the Scrum Team. | PSM I Assessment
The Developers try to put together some guidelines on testing approach. Who will own these guidelines? | multiple-choice | Developers | Test Lead | Scrum Master |  |  |  | 1 | The testing approach is part of development work. The development work is owned by the Developers. | PSM I Assessment
During a Sprint Review, the Scrum Master notices that the Product Owner does not use the Product burn-down graph to explain the status to the stakeholders. The Scrum Master | multiple-choice | Should coach the Product Owner on the importance of using this Scrum tool | Should cancel the Sprint Review and schedule it back when the Product Owner is ready with this tool | Do Nothing |  |  |  | 3 | There are many tools like product burn-down that help to show the evolution of the past and its projection into future. While they are useful, none of these tools are mandated by Scrum. Scrum Master should strive to coach the team about importance of empiricism and not the tools. | PSM I Assessment
The Scrum Master manages | multiple-choice | Scrum People | Scrum Framework | Scrum Technology | All of them | None of them |  | 2 | Scrum Master is not a people manager. Scrum does not prescribe any technology. Scrum is container framework within which techniques and technologies can be employed to develop complex products. | PSM I Assessment
A Scrum Team decides to have an exclusive Sprint to evolve the technical architecture. The sole outcome of this Sprint is a finalized architecture design. | multiple-choice | It is a good practice since it will help the design to emerge | It is not the Scrum approach, since every Sprint must produce at least one releasable functionality | It does not matter, since the team is self-managing about how to perform their work |  |  |  | 2 | In Scrum, technical architecture is evolved continuously throughout the project, as more is learned. There is no exclusive Sprint or Scrum event to define the technical architecture upfront. Usually the Developers define architectural guidelines that every team member can use in their work. The team can also have core hours to review the design and architecture during the Sprint. As a result, these guidelines are continually updated, and the technical design emerges on the go. | PSM I Assessment
The Scrum Team, based on the learning from previous Sprints, decides to revisit the length of the Sprint. What is the appropriate Scrum event to discuss and agree on the change? | multiple-choice | Scrum Planning | Sprint Planning | Retrospective | Daily Scrum |  |  | 3 | Retrospective is an event where the team inspects their way of working (people, relationships, processes, and tools), and adapts any improvements. | PSM I Assessment
The Developers can deliver an Increment that meets the Definition of Done, but the Increment still can have defects that are known to the team and the Product Owner. | multiple-choice | Yes | No |  |  |  |  | 1 | An Increment can have known gaps but must meet the Definition of Done. The reason for having a lenient Definition of Done is - Definition of Done should contain conditions that are realistic to achieve for the team. For newer teams, they can start with a realistic (feasible for the team) Definition of Done, and then can be continually be improved by maturing team's ability to perform all that is required to deliver flawless Product Increment. Having a realistic Definition of Done for newer team means that the working Increment may have known bugs. But such gaps are transparent between the Developers and Product Owner. | PSM I Assessment
The Developers have not completed any of the Product Backlog Items selected for the Sprint by Sprint end. Next step is Next step is | multiple-choice | Extend the Sprint since Scrum favors "getting done” | Advice the Product Owner to accept the completed portion of the incomplete Product Backlog Items, and plan to complete them by next Sprint, since Scrum favors "empowered teams” | End the Sprint with a Retrospective, since Scrum favors "time boxing” |  |  |  | 3 | The Scrum events are strictly time boxed. They end as per the time box no matter what. | PSM I Assessment
Select all that apply. The Sprint Review is an event that requires | multi-select | Product Owner’s sign-off | Stakeholders active participation | Transition sign off | Inspection and Adaptation activities |  |  | 2,4 | Sprint Review is an informal meeting, not a status meeting, and the presentation of the Increment is intended to elicit feedback and foster collaboration. There are no sign-offs. | PSM I Assessment
Only the Product Owner can come up with items that can be considered for Product Backlog. Others cannot provide input / recommendations / ideas about new items | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | While the Product Owner has the final say on the content and order of the Product Backlog, he can still get the input / recommendations / ideas about new items from any stakeholders for consideration. | PSM I Assessment
A Scrum Team needs to develop a web application in Increments. Some of the Sprints have Sprint Goals like this: ‘Develop Data layer for Functionality A’. What is your inference? | multiple-choice | The Scrum Team follows horizontal decomposition of the Product Backlog Items. This is recommended | The Scrum Team follows vertical decomposition of the Product Backlog Items. This is recommended | The Scrum Team follows horizontal decomposition of the Product Backlog Items. This is NOT recommended | The Scrum Team follows vertical decomposition of the Product Backlog Items. This is NOT recommended |  |  | 3 | It is preferable to decompose the Product Backlog Items such that each team can produce fully working business functionality on its own rather than producing a technical component. Such decomposition is called as vertical decomposition. A horizontal decomposition on the other hand makes the team depend on other teams to integrate and create a fully working business functionality. Such teams usually end up as just technical component teams. | PSM I Assessment
Select all that apply. During the Daily Scrum, the Scrum Master's role is to: | multi-select | Facilitate discussions of the Developers | Moderate and control so that everyone gets a fair chance to speak | Ensure that all 3 questions have been answered | Teach the Developers to keep the Daily Scrum within the 15 minute time box | All of the above |  | 1,4 | Scrum Master facilitates the Scrum events as and when requested by others or required by their observations. Scrum Master does not take any active role in directing or controlling the Daily Scrum. It is up to the Developers to fully leverage it for their synchronization and progress. Scrum Master is the guardian the Scrum process and time boxing is a cardinal rule of Scrum. So, Scrum Master coaches the team to keep the Scrum rules. | PSM I Assessment
Middle of the Scrum, the team comes to know that there are some usage related changes to the Product needs. The Product Backlog | multiple-choice | Is modified to reflect the new need | Is closed. Project is cancelled and new Product Backlog will be built | Is not impacted and the Sprints continued |  |  |  | 1 | The Product Backlog is never complete during the project. It undergoes constant changes and continuously refined. It exploits emerging opportunities and adjusts the emerging risks, so the value can be optimized. | PSM I Assessment
Three Scrum Teams are working as part of a big project to develop a product. When Sprints are in motion, there will be | multiple-choice | Three Product Backlogs, and three Sprint Backlogs | One Product Backlog, and three Sprint Backlogs | One Product Backlog and one Sprint Backlog |  |  |  | 2 | Since all of them work on a single product, there will be one common Product Backlog. But each Scrum Team will have its own Sprint Backlog and Sprint Goal. | PSM I Assessment
In a Scrum based software project, "Earned Value" is a good metric to track product development progress | multiple-choice | Yes | No |  |  |  |  | 2 | The real mark of progress in Scrum is - the delivery of useable product Increment in every Sprint. | PSM I Assessment
Effort required to fix/refactor something after it has been built is known as | multiple-choice | Maintenance | Technical Debt | Plumbing code |  |  |  | 2 | Technical debt is not a concept within Scrum. However, it is commonly used by Scrum Teams to indicate the gap unaddressed in a done Increment. | PSM I Assessment
Usually, when Scrum is applied newly in an organization, | multiple-choice | Power of empiricism will be transparent | Everything that impedes producing value in short Sprints and accumulation of waste will be made transparent | The organization change management process defined by Scrum should be followed to avoid implementation issues |  |  |  | 2 | Scrum will expose all weakness in the current eco-system that need to be resolved. Scrum does not define any organization change management process. | PSM I Assessment
How are the Non Functional Requirements addressed by the Scrum Team? | multiple-choice | by testing them in 'Hardening Sprint' | by ensuring that they are met by every Increment and typically defining them in the Definition of Done | By having a Non Functional System Team owning them |  |  |  | 2 | Definition of Done defines the standards to be met for a Product Backlog item to be considered as Done. Typically, Non-Functional Requirements are added to the Definition of Done so that such requirements are built into every Increment. | PSM I Assessment
A Scrum Team often runs into following issues: Conflicting requirements from different departments, ad-hoc work requests from different business managers, no feedback on Increments. What could be the likely cause? | multiple-choice | Issues with how Scrum Master guides the team | Issues with Product Owner responsibilities | Issues with planning abilities of the Developers |  |  |  | 2 | All these issues have something to do with collaborating with business stakeholders, maintaining Product Backlog, participating in Scrum events, etc. These are Product Owner’s responsibilities. | PSM I Assessment
In Scrum based software development effort, while the Sprint Goal will deliver a Product Increment, one of the Product Backlog Items is asking for production of a document. | multiple-choice | It is not okay. Every Product Backlog item must be about a working software requirement | It is not okay. Documentation is not needed until Product Owner chooses to release an Increment to production | It is okay. A Sprint can produce a document as a sole outcome of the Sprint | It is okay. A Sprint can produce other deliverables like document requested by Product Owner along with working Increment |  |  | 4 | While the Sprint must necessarily produce a valuable and useful Increment, some of the Product Backlog Items could produce other deliverables including documents if the Product Owner considers them having appropriate value. If a Product Backlog item is a document, it may not be subjected to Definition of Done which is usually the standards needed for software. So, while the Definition of Done is applicable at Increment level, it may not be applicable for some individual Product Backlog Items. | PSM I Assessment
Shortly into using Scrum for the first time in an organization, the Scrum Team runs into several impediments in following Scrum. The most common inference is | multiple-choice | Scrum does not work for their organization | The Scrum Team didn’t plan the project end-to-end well in advance | It is normal for first timers. Scrum will expose all weakness in the current eco system that impede developing Product Increments in short Sprints. |  |  |  | 3 | Scrum will expose all weakness in the current eco system that need to be acknowledged and resolved by the organization. | PSM I Assessment
In empiricism, the decisions are based on | multiple-choice | Scientific calculation and Prediction | Meeting and Brainstorming | Observation, experience, and experimentation |  |  |  | 3 | Empiricism is a process control theory in which only the past is accepted as certain and in which decisions are based on observation, experience, and experimentation. | PSM I Assessment
The standard used by the Product Owner and the Scrum Team to identify unfinished work in a Sprint is | multiple-choice | Coding Standard | Definition of Ready | Testing Standard | Definition of Done |  |  | 4 | Definition of Done provides the common understanding to the Scrum Team about how to assess the completion of a Product Backlog item or the Increment. | PSM I Assessment
Select all that apply. The mandatory participants of the Sprint Retrospective meeting are | multi-select | Product Owner | Stakeholders invited by Product Owner | Scrum Master | Developers | Technical/Domain/Process experts invited by Scrum Team |  | 1,3,4 | Retrospective is an opportunity for the Scrum Team to inspect and adapt the Scrum Team itself. | PSM I Assessment
Pick the Scrum Values | multi-select | Respect and courage | Simplicity | Commitment and Openness | Creativity and Intuition | Focus |  | 1,3,5 | Other answers also reflect Scrum. However, these five are the Scrum Values as defined in The Scrum Guide. | PSM I Assessment
The Scrum Team gathers for Sprint Planning meeting. The Product Owner has some Product Backlog Items but the Developers find that they do not provide enough information to understand the work involved to make forecast. The next best thing to do is | multiple-choice | The Scrum Master cancels the Sprint | The Developers proceed with starting with whatever is known | The Developers make it transparent that they cannot make a forecast with insufficient information, and negotiate with Product Owner on refining the Product Backlog Items to ready state | The Scrum Team discusses the root cause in the Retrospective |  |  | 3 | The Developers should maintain highest transparency while making a forecast of the work that they believe they could complete. In this case, they cannot do that because the Product Backlog Items do not provide enough information. So, they have to utilize the time available to refine the items to required state and proceed with plan. Later, in the Retrospective the Scrum does discuss the root cause and hence answer ‘d’ is also correct. But the question asks about “next best thing to do.” | PSM I Assessment
The process of the coming into existence or prominence of new facts or new knowledge, or knowledge of a fact becoming visible unexpectedly, is called as | multiple-choice | Transparency | Inspection | Emergence |  |  |  | 3 |  | PSM I Assessment
Sprint Planning is the only occasion where the Developers estimate the Product Backlog Items | multiple-choice | True, because without estimate, the team cannot plan what can go into the Sprint | False, estimation of Product Backlog Items is a continuous event throughout |  |  |  |  | 2 | Every item in Product Backlog needs to have a description, order, value, and estimate. The Product Owner works with the Developers throughout in Backlog Refinement sessions, to refine the backlog items and get the estimate. | PSM I Assessment
Scrum is immutable. What may be the result of an organization modifying Scrum Framework in its implementation for the convenience of existing culture? | multiple-choice | The organization may lose the opportunity to expose its current cultural dysfunctions that impede the ability to develop the Product Increment Sprint after Sprint. | Scrum is bound by technical tools and these tools will break | It can only be done with the help of Scrum coaches |  |  |  | 1 | Scrum does not prescribe or mandate any tools. There is no role such as Scrum coach. | PSM I Assessment
A Scrum Team has technical specialists in its composition. The specialists perform their work when the Sprint Backlog needs their special skills, but they are idle otherwise. | multiple-choice | Continue to have the specialists to deliver fully integrated Increments. Gradually facilitate the Developers to organize their work to fully leverage these special skills. If required, the team can enhance everybody’s domain of expertise, so everyone is productive as team without idle time | Let the project manager coordinate their staffing needs and plan partial allocations to different teams to avoid idle time | Defer and accumulate the special work to later Sprints until it needs full time specialists. Deliver the Increment with workarounds. Later, when specialists are added, refactor the Increment removing the workarounds so it can become releasable. |  |  |  | 1 | There is no project manager role in Scrum and the Developers manage their own development work. A Scrum Team must be cross functional enough, that is, it should have all required special skills, without the need for any external help in completing the Sprint Backlog. | PSM I Assessment
The Sprint Review is an opportunity to review | multiple-choice | Timeline and Budget | Defects and causes | Requirements and Capacity | All of the above |  |  | 1 | Sprint Review is a Scrum event that offers an opportunity to inspect and adapt. Stakeholders collaborate to review the timeline, budget, potential capabilities, and marketplace for the next anticipated release of the product. The team also explains what happened during the Sprint. But they do not inspect about the defect and causes. | PSM I Assessment
Definition of Done is | multiple-choice | Testing strategy for Scrum Team | A standard used by Scrum Team to assess if a product Increment is Done | Defined by Product Owner and safeguarded by Scrum Master |  |  |  | 2 |  | PSM I Assessment
A person external to the Scrum Team with a specific interest in and knowledge of a product that is required for Incremental discovery, is known as | multiple-choice | Technical/Domain Expert | Stakeholder | Senior Management |  |  |  | 2 | Though stakeholder is generally regarded as those having some interest in the product, Scrum has this specific definition of the stakeholder. | PSM I Assessment
Sprint Backlog is modified throughout the Sprint. As soon as a new task is identified, | multiple-choice | Product Owner adds it to the Sprint Backlog and communicates about it to Scrum Team | Scrum Master adds it to the Sprint Backlog and communicates about it to Scrum Team | Developers add it to the Sprint Backlog and communicate about it to Scrum Team |  |  |  | 3 | The Developers own the Sprint Backlog. | PSM I Assessment
On their kick-off day, a new Scrum Team didn’t have any Scrum tool. The next best thing to do is | multiple-choice | Expedite the installation of tool before the close of iteration zero | Get the recommendation from Product Owner about how to manage Scrum artifacts without the tool | Do nothing. Implementatio of Scrum does not require any tool |  |  |  | 3 | Implementation of Scrum does not require any tool. | PSM I Assessment
The selection of items from the Product Backlog that the Developers deem feasible for implementation in a Sprint is called | multiple-choice | Estimation | Planning Poker | Forecast of functionality |  |  |  | 3 |  | PSM I Assessment
An Organization needs to structure hundreds of Developers into Scrum Teams. You as a Scrum Master will | multiple-choice | work with the organization management and prepare the best structure for each Scrum Team based on the seniority and skills of the Developers | identify required number of Scrum Masters and require them to choose their Scrum Teams | facilitate the awareness of the Developers about the goals and objectives of the product development, coach them about Scrum, and let them work among themselves to form the Scrum Teams |  |  |  | 3 | Scrum Teams are self managing teams. Given the knowledge of the product vision and sound understanding of how Scrum works, the team is knowledgeable enough to form themselves into Scrum Teams. A Scrum Master needs to facilitate this. | PSM I Assessment
Middle of the Sprint, the Developers find that some of the Product Backlog Items forecast for this Sprint cannot be finished because they need significant additional effort. However, they “can still meet Sprint Goal with rest of the items. The next thing to do is” | multiple-choice | Consult with Product Owner and if they agree, have them cancel the current Sprint, and plan new Sprint with new estimations | Do not cancel or modify the Sprint. Extend the Sprint duration as required for the additional effort | Collaborate with the Product Owner to remove the Product Backlog Items that cannot progress, and new work up to team’s capacity. Complete the Sprint. |  |  |  | 3 | Cancelation of the Sprint is decided by Product Owner, and Product Owner will not cancel the Sprint unless the Sprint Goal becomes obsolete. Here the Sprint Goal is intact. Also, the Sprint duration cannot be extended since it is time boxed. | PSM I Assessment
Sprint Planning helps in | multiple-choice | Building entire technical architecture | Staffing plan | Testing strategy | Release plan | None of the above |  | 5 | Sprint Planning is focused on coming up with Sprint Backlog and Sprint Goal. Sprint Backlog consists of work planned for that Sprint, the plan to achieve that work, and one or more team improvement items. Technical architecture is evolved over the Sprints. | PSM I Assessment
Which is true? | multiple-choice | Sprint Retrospective focuses on Product and Sprint Review focuses on development processes | Sprint Retrospective focuses on development processes and Sprint Review focuses on Velocity | Sprint Retrospective focuses on development processes and Sprint Review focuses on Product |  |  |  | 3 | Sprint Review is a Scrum event to inspect and adapt the product development. Sprint Retrospective focuses on inspecting and adapting the way of working to develop the product. | PSM I Assessment
Team Velocity refers to | multiple-choice | Average of amount of Product Backlog Items turned into Done Items per Sprint | Average rate of churn of team members in Scrum Team during a Sprint | Average number of defects per Sprint normalized over all defect types |  |  |  | 1 |  | PSM I Assessment
In a new Scrum Team, a Scrum Master notices that a Developer works on a task that is not contributing to the Sprint Goal or the Sprint Backlog. The Scrum Master | multiple-choice | Should escalate this to Product Owner | Should discuss with team member and educate about Scrum way of working | Should not interrupt since the team is self-managing |  |  |  | 2 | The Scrum Master does not manage people. They encourage the self-management of the team to manage its work. However, the Scrum Master is the guardian of the Scrum framework and hence its rules. The Developers should only work on tasks related to Sprint Goal. When there is a violation, Scrum Master actively steps in to coach the team on Scrum. | PSM I Assessment
The role of Scrum Master with respect to Scrum artifacts is | multiple-choice | Coach the team to increase the transparency of the artifacts | Decide the format of the artifacts and ensures that the team follows it | Owner of the artifacts and responsible for having them up to date |  |  |  | 1 |  | PSM I Assessment
Select all that apply. It is essential for the Product Owner to have these skills. Usually Scrum Master serves the Product Owner by coaching them | multi-select | Software application development | Understanding and practicing agility | Coaching team | Product planning in empirical environments |  |  | 2,4 | Product Owner must have the understanding to perform product planning in empirical environment, and practicing agility. Scrum Master serves the Product Owner by coaching them these skills. | PSM I Assessment
The estimation method recommended by Scrum is | multiple-choice | Planning Poker | T-Shirt Sizing | Yesterday’s weather | None of the above |  |  | 4 | Scrum does not prescribe any specific estimation technique. | PSM I Assessment
Under this topic of the Sprint Planning, the Developers are more active in planning and Product Owner is mostly observing or clarifying | multiple-choice | Topic One (Why) | Topic Two (What) | Topic Three (How) |  |  |  | 3 | In topic three, the Developers put together a plan of how to achieve the scope of the Sprint. It primarily involves deriving work tasks. Since they are accountable to complete these tasks, they are more active during topic three. | PSM I Assessment
A good guideline to differentiate Acceptance Criteria from Definition of Done is- Definition of Done provides checklist of quality measures to take the Increment close to usable state, while Acceptance Criteria specify the business functionality | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | Definition of Done is a standard to define the quality measures required for a useful product. Acceptance criteria is the specification of expected business features (functionality) of the product. | PSM I Assessment
The Developers of a Scrum Team often get some production support requirements, in addition to the work in the Sprint Backlog. The team adapted their team composition and created an exclusive sub team to support these ad-hoc requirements. | multiple-choice | It is okay to create sub team within Scrum | It is not okay since there cannot be sub teams within the Scrum Team. | The team can complete the production support as one team, since it is high priority, and then come back to original Sprint work | It is okay if it is explicitly approved by Scrum Master |  |  | 2 | Every Sprint is meant for delivering an Increment of releasable software / product, as required in Sprint Goal. If an outside item is taking the team’s time, it is treated as an issue. If the team is forced by any authority, Scrum Master needs to coach these external authorities about how Scrum works and facilitate removing this issue. | PSM I Assessment
Select all that apply. The Developers are accountable for | multi-select | Selecting the Product Backlog Items for the Sprint after clarifying with the Product Owner | Reporting to the Scrum Master | Creating a valuable and useful Increment every Sprint | Increasing the productivity as per management goal |  |  | 1,3 |  | PSM I Assessment
The Developers meet every day to inspect the progress and adapt the next day plan. If the Daily Scrum exposes the need to re-plan rest of the Sprint, these re-planning activities happen | multiple-choice | During the Daily Scrum | Immediately after the Daily Scrum | As soon as the team gets some extra time | The Sprint plan cannot be revised except during Sprint Planning |  |  | 2 | The Developers use the Daily Scrum to inspect progress towards the Sprint Goal and to inspect how progress is trending towards completing the work in the Sprint Backlog. During the Daily Scrum they come up with the next 24 hour plan. But, if they see that the entire Sprint plan needs a revisit, they meet immediately after the Daily Scrum for detailed discussions, or to adapt, or re plan, the rest of the Sprint’s work. | PSM I Assessment
It is mandatory that the Definition of Done includes “Release to Production” | multiple-choice | Yes | No |  |  |  |  | 2 | Every Sprint includes producing a valuable and useful Increment. However, it is Product Owner’s call to release that to production. | PSM I Assessment
Burn-up and Burn-down charts show evolution of progress over time. In particular, | multiple-choice | Burn-up shows increase in completion, while Burn-down shows remaining effort | Burn-up shows increase in team productivity, while Burn down shows decrease in productivity | Burn-up shows increase in turn around time, while Burn-down shows decrease in turn-around time |  |  |  | 1 | Both burn-up and burn-down are not mandatory but optional in Scrum. They are used to make the progress transparent. | PSM I Assessment
When can a Product Owner negotiate the scope of what the team will work on next? | multiple-choice | Anytime during the current Sprint with or without Developers’ consent | Until the Sprint Planning for the current Sprint | Both |  |  |  | 2 | Scrum allows the Product Owner to decide what the team will work on next by ordering the Product Backlog Items. In Sprint Planning, the team picks up these backlog items as the scope of the Sprint. However, after the Sprint Planning and until the Sprint end, the Product Owner cannot correct the Sprint Backlog without the Developers’ consent. | PSM I Assessment
An organization is on its path to adopt Scrum as its approach to software development. It decides to convert all Project Managers into Scrum Masters. | multiple-choice | It is good strategy. The project managers already know how to run projects. They just need training on Scrum | It will create resentment to project managers, because they will have a small team to manage | The organization needs to rethink on this strategy. Identifying persons who are inclined or experienced in coaching and facilitation as their leadership style is a better strategy. |  |  |  | 3 | Scrum Master does not manage any team. The Scrum manager is not required to know project management since it is shared between three roles of Scrum. | PSM I Assessment
The Scrum Team optimizes the following and deliver business value | multiple-choice | Flexibility, creativity, and productivity | Self-Improvement, Leadership, Motivation | Individual Power, Heroic Efforts, Recognition |  |  |  | 1 | The Scrum framework is a collaboration framework within which Scrum Team can creatively and productively deliver business value with quality. The team model in Scrum is designed to optimize flexibility, creativity, and productivity. | PSM I Assessment
What is the correct statement? | multiple-choice | The technical design continuously evolves over the Sprints. Hence the team should have some basic guidelines to start with, but try to emerge the design through the Sprints. | The team can choose to have an exclusive Sprint only to finalize the technical design. At the end, the design should be approved by the project architect | The team does not need to pay attention on the architecture as it will evolve itself as a by-product of self-management |  |  |  | 1 | There is no exclusive Sprint only to finalize the design. Every Sprint must be used to produce at least one working functionality that is valuable and useful. | PSM I Assessment
A Scrum Team has five members. Each one works on a different product. What could we infer about the team? | multiple-choice | The team will have higher productivity since division of work is clear | The team implements diversity, a principle of Scrum | The potential of teamwork and benefit of Scrum is less | All of them still will have common Definition of Done |  |  | 3 | Since everyone is working on a different product, there is minimal chance of teamwork, collaboration, and team self management. | PSM I Assessment
In the middle of the Sprint, the Developers find that few more days of work is needed to complete the scope. The planning options include: | multiple-choice | Add more team members | Catch up using weekends | Defer the activities like testing after stakeholder’s demo | Involve the Product Owner and negotiate alternatives | All of the above |  | 4 | Scrum events are time boxed. Sprint needs to be over by defined date. However, the scope of the Sprint may expand or contract as more is learned throughout the Sprint. When new issues emerge that threaten the completion of Sprint by pre set date- As a first step, the team needs to capture this as an issue and try to solve on their own. If they cannot, they should make this impediment transparent and take Scrum Master’s help. Even after that, if the impediment is not solved, they need to involve the Product Owner to discuss the alternatives. | PSM I Assessment
The Sprint Backlog emerges during the Sprint because the Developers modify it throughout the Sprint. In the middle of the Sprint, new work is added to Sprint Backlog. As a result, estimated remaining work will | multiple-choice | Increase | Decrease | Stay the same |  |  |  | 1 | The Sprint estimation is not necessarily constant. As more is learned, the work is adjusted. When new work is added, it increases the amount of remaining work. | PSM I Assessment
In the middle of the Sprint, the Developers did not get some technical tools that were originally promised. This will slow down the work. The next best thing to do is | multiple-choice | Scrum Master should escalate to Project Manager | Product Owner should cancel the Sprint | The Developers should assess the impact to meeting the Sprint Goal and the Definition of Done, and find alternatives to still meet the Sprint Goal without compromising the Definition of Done |  |  |  | 3 | The first step is to self-manage the issue and find work-around to preserve the Sprint Goal completion. If that does not solve the issue, it needs to be raised as an impediment seeking Scrum Master’s help. | PSM I Assessment
When a Scrum Team adds new team members for replacing some members going out, the productivity of the team | multiple-choice | Will be negatively impacted | Will be positively impacted | Will remain the same |  |  |  | 1 | When new team members join, the productivity of the team will be temporarily reduced. | PSM I Assessment
The Developers are not having regular (Daily) Scrums. As a Scrum Master, you | multiple-choice | Will advise them to think about conducting regular Scrums, but will let them take the decision themselves as they are self managing | Will escalate this to resource managers | Will step in directly to guard the Scrum Framework by asking action begetting questions to team and positively influencing them to conduct Scrum events |  |  |  | 3 | The Scrum Master does not manage people. They encourage the self-management of the team to manage its work. However, the Scrum Master is the guardian of the Scrum framework and hence its rules. Daily Scrum is an opportunity to inspect and adapt daily progress, so that the work-related differences are not allowed to go beyond a day. When there is a violation, Scrum Master actively steps in to coach the team on Scrum. | PSM I Assessment
Scrum framework is used to optimize value and control risk in complex product development. A component of value optimization is | multiple-choice | Averaging out the values delivered over Sprints and use it to take decisions | Deciding to continue a Sprint only after verifying if it has enough value worth the effort | Ensuring that the Developers are not having idle time by constantly monitoring their productivity |  |  |  | 2 | It is the responsibility of the Product Owner to verify that a Sprint has enough value to worth the effort. They are rigorous value optimizers. | PSM I Assessment
During Sprints, the Developers of a Scrum Team need to wait for another team to provide some dependent input. Often this leads to delay in completing their work. What can be recommended to this team? | multiple-choice | The team is not cross functional enough. The team should take Scrum Master's help in educating the organization to add team members with appropriate skills | The team should agree on Service Level Agreement (SLA) with another team and escalate to Scrum Master if the SLA breached | The team can mock up the sample of input instead of waiting and do the Sprint Review on time. The Product Increment can be refactored as and when another team provides input. |  |  |  | 1 | A Scrum Team should be cross functional enough, i.e., should have all the skills needed to convert the Product Backlog Items into Done Increment. If the team needs to depend on external entities for converting backlog items into done Increment, it is not cross functional enough. Every Sprint outcome should be valuable and useful. Mocking up does not complete the work as per that standard. | PSM I Assessment
A Scrum Team develops software. Only when the Product Owner decides to go for the release, the team creates end user documentation for the Product Increment at that point. | multiple-choice | It is correct. Creating document early will require constant effort to keep them updated. | It is correct. Scrum favors less documentation and deferring the decision to last minute. | It is incorrect. Anything required for the Product Increment to be valuable and useful (potentially releasable to production) is recommended to be part of Definition of Done. |  |  |  | 3 | Every Increment is a valuable and useful Increment. It means that whatever is required for the release, it should be defined as part of Definition of Done. For a Product Backlog item to be considered as ‘complete’, it must meet this Definition of Done. | PSM I Assessment
A Scrum Team has following condition under the Definition of Done: “All the code to be reviewed and approved by Industry Coding Standard Organization.” This Industry Coding Standard Organization is a third-party Subject Matter Expert outside Scrum Team. | multiple-choice | The Definition of Done is less effective, because it contains conditions that is not completely within influence of the Scrum Team | The Definition of Done is more effective, because it ensures that required standards are met | The Definition of Done can contain anything as decided by Product Owner |  |  |  | 1 | The activities required to complete the Product Backlog Items to a Done state should be completely within the ownership and influence of the Scrum Team. | PSM I Assessment
The Developers of a Scrum Team have created the Sprint Backlog in the form of a task board. What is your inference? | multiple-choice | The team can choose to represent it any form that makes sense | It is okay to have it in task board format, but it must be ensured that it follows Kanban guidelines | Scrum Master must coach the team to create proper Sprint Backlog in the form of list of backlog items, related tasks, and estimations |  |  |  | 1 | Sprint Backlog contains the Product Backlog Items for the current Sprint, and the plan to complete and realize the Sprint Goal. Scrum does not prescribe any specific format or technique to be followed for representing Sprint Backlog. | PSM I Assessment
In the middle of the Sprint, the Developers find that they have more capacity to take more work. The next best thing to do is | multiple-choice | Make it transparent to Product Owner immediately and collaborate to add additional work. | Consult and follow Scrum Master’s and follow their direction | Keep that as a contingency to accommodate unplanned work |  |  |  | 1 | Scrum events are time boxed. Sprint needs to be over by defined date. However, the scope of the Sprint may expand or contract as more is learned throughout the Sprint. When the work gets contracted due the new findings, and there is more room for additional work, the team makes it transparent to the Product Owner. Scrum Master mentors the team to increase such transparency. | PSM I Assessment
What is the desirable team composition for large product development program? | multiple-choice | Program is divided into individual Scrums based on business feature. Each Scrum Team has all the skills needed to finish job without external help | Program is divided into individual Scrums based on technical components. Each Scrum Team has its component specific skills needed to finish their own component without external help | Program is organized into consumer Scrums and service provider Scrums (front end could be consumer who plays as Product Owner to a middle tier Scrum). Each Scrum gets the dependencies work done leveraging their Product Owner position |  |  |  | 1 | It is preferable to divide teams such that each team has absolute ownership of their work without external dependencies. | PSM I Assessment